## PDSA Cycle – Essential Eight Cyber Security Improvement

Organisation: Bay Centre Medical
Assessment Date: 13 June 2025
Assessor: NoDa (Northern Data) 
Focus Area: Implementation of ACSC Essential Eight Controls
Current State: Maturity Level 0 across all domains

This PDSA was established after completing a third party assessment, undertaken by external assessor NoDa (Northern Data). The findings report provided post-assessment has helped inform our PDSA.

### 1. PLAN

Objective:
To establish foundational cyber security controls aligned with the ACSC Essential Eight framework, moving Bay Medical from Maturity Level 0 to Level 1 within 12 months.

Goals:

- Reduce cyber risk exposure by implementing baseline controls.

- Develop formal policies and governance for patching, access control, and backup.

- Build organisational awareness and accountability for cyber resilience.

Key Actions (Planned):

| Area | Planned Action | Responsible | Timeline |
| --- | --- | --- | --- |
| Governance | Develop and approve cyber security policies (Application Control, Patch Management, Access Control, Backup). | IT Manager / Executive Team | Q1 |
| Application Control | Implement whitelisting and maintain approved application list. | IT Administrator | Q2 |
| Patch Management | Configure automated patching for applications and OS via Intune or equivalent. | IT / External MSSP | Q2 |
| Privileged Access | Review and restrict admin privileges; apply least-privilege principle. | IT / HR | Q2 |
| MFA | Enforce multi-factor authentication for all critical systems and remote access. | IT | Q2–Q3 |
| Backup & Recovery | Verify backup integrity monthly and test recovery procedures quarterly. | IT / Compliance | Q3 |
| Training | Roll out mandatory cyber awareness program for all staff. | HR / IT | Q3 |
| Monitoring | Establish regular review and reporting on Essential Eight maturity progress. | Cybersecurity Lead | Q4 |

Expected Outcome:
A measurable increase in cyber security maturity and compliance readiness (targeting Level 1).

### 2. DO

Implementation Steps Taken:

- Initiate Essential Eight Implementation Project under IT governance.

- Engage external cyber security consultant/MSSP for technical configuration and validation.

- Conduct internal communication to raise awareness about upcoming changes.

- Begin policy drafting and approval process.

- Pilot MFA deployment for administrative accounts and remote access users.

Documentation:

- Policy drafts

- Change control records

- MFA rollout logs

- Patch deployment schedules

### 3. STUDY

Evaluation Methods:

- Conduct internal audits to measure progress against Essential Eight controls.

- Review system and patch compliance reports.

- Assess staff participation and performance in awareness training.

- Validate backup tests and recovery simulations.

- Review findings with executive management and cybersecurity consultant.

Indicators of Success:

| Metric | Baseline | Target | Measured Outcome |
| --- | --- | --- | --- |
| Systems patched within 14 days | <30% | 100% | TBD after 6 months |
| MFA enforcement | 0% | 100% | TBD after 6 months |
| Documented policies approved | 0 | 5 core policies | TBD |
| Backup recovery success rate | Not tested | 100% verified quarterly | TBD |
| Staff trained in cyber awareness | 0% | 100% | TBD |

### 4. ACT

Adjustments / Next Steps:

- Address gaps identified during internal review (e.g. incomplete MFA rollout, patch compliance issues).

- Update policies and training based on feedback and lessons learned.

- Schedule a Stage 2 Assessment to confirm uplift to Maturity Level 1.

- Plan for next phase of improvements toward Maturity Level 2 (enhanced security monitoring and control).

Sustainment Actions:

- Embed cyber security KPIs in organisational performance reviews.

- Establish quarterly security governance meetings.

- Continue periodic internal and external audits.

### Outcome Goal

By the end of the first 12-month cycle, Bay Medical will have:
✅ Implemented baseline Essential Eight controls (Maturity Level 1)
✅ Reduced exposure to common cyber threats
✅ Established a culture of cyber awareness and accountability